OpenShift PoC for MitziCom
Scoping and Engagement Plan
Sebastian Hetze
Solution Architect, Red Hat
June 17th 2018
[Speaker Notes: The Engagement Plan serves as communication format to make sure we have a common understanding what has to be done. We call this Engagement Plan (not Project Plan, Proposal, Scoping, ...) for a reason. Usually, from a customer perspective our endeavor is either part of a product purchase or some sort of outsourced operational task (OpEx vs CapEx), so this should not be called a project. However, this is a planning document that goes beyond the scoping. The Solution Architect picks up a RT ticket and calls the customer to gain a comprehensive understanding of the customer needs, he then plans and discusses the possible solution (using Red Hat products and services). This template serves as a guideline to make sure all relevant aspects to this planning are covered in the communication. Not every slide needs to be edited, some slides may be deleted (instructions how to use each slide in the Notes). In any case, every slide topic should at least be thought about and if in doubt proactively discussed with the customer.]

---
Disclaimer
The purpose of this document is to build a common understanding of a business need or problem MitziCom currently has and to describe a intended solution, using Red Hat products and technology.
The information provided in this document is non-binding.
This document is neither a contract nor an offer that could be accepted by the other party. If the parties decide to enter into a business relationship, they will memorialize the terms of that relationship in a separate agreement between them or their respective business partners.
[Speaker Notes: The <customer> name needs to be replaced here. This slide is mandatory to emphasize the non binding character of this document. Wording is conforming to https://mojo.redhat.com/docs/DOC-980697]

---
Problem Statement
1. MitziCom provides hosting and cloud services to a variety of clients, from medium size companies to enterprise giants.
2. Business Owners and Customers demand MitziCom to provide a Container PaaS for internal and client workloads.
[Speaker Notes: This slide serves two purposes: First, if we start with a good opening statement that hits the nail on its head, the customer instantly gains confidence and trust. Second, this short statement helps classifying engagements to make this planning document reusable. So please take your time and boil down the whole thing to one or two sentences. This may well be done after writing the comprehensive Problem Description on the next slide.]

---
Problem Description
MitziCom needs to deploy and operate a Container PaaS in a highly automated and HA fashion.
CI/CD workflows have to be eanabled in a secure multitenant aware setup.
Resources have to be managed using self service capabilities and quotas.
[Speaker Notes: The problem description summarizes all information the customer has given in the call/meeting about the reasoning for his request. This description may go well beyond the actual scope of our engagement. We may only be able to provide a small part for a solution. However, it is important for the Consultant to understand the problem in a broader context. And the customer once again gains confidence and trust if we demonstrate a deep understanding of the problem. This part is mandatory and may be extended if necessary.]

---
Solution Architecture
Red Hat will perform a PoC with the customer to demonstrate strenghts and limitations of Red Hat OpenShift Container Platform in order to determine the feasibility of using Red Hat OpenShift Container Platform as target for internal and client workloads.
[Speaker Notes: The Solution Architecture provides the link between the customer pain / problem description of the previous slide and the actual engagement scoping on the next slide. Here we describe the solution. You may consider adding a second variant of your proposed solution, leading to a duplicate WBS with two effort estimates. This part is mandatory and may be extended if necessary.]

---
Scope
This section provides a high-level description of the features and functions that characterize the product, service, or result that the engagement is meant to deliver
- High Level Requirements
- Major Outcomes
- Boundaries
- Define what is explicitly out of scope
[Speaker Notes: This slide describes what is in scope and (even more important) what is out of scope for this engagement. The previous architecture slide(s) may describe a much broader solution. This scoping slide allows to narrow down the scope of this particular engagement. This part is mandatory and may be extended if necessary. The out of scope declaration is crucial and mandatory aswell! Engagement / Project type	Assessments & Architectural Services	Red Hat owns Complete Project Responsibility	Red Hat owns Complete Project Responsibility		Classical Professional Services / (Installs, Break & Fix, POC, Product adoption except pure DEE engagements) <=30 days	>30 days	<=20 days	>20 days Team Setup	Individual scoping & setup with the rough rule of approx. / 20% PM and 50%-100% Architect	Individual scoping & Setup with the requirement of approx. / 40% - 60% PM / 40% - 60% Architect	Individual scoping & Setup with the requirement of approx. / 20% PM and / 20% - 40% Architect	Individual scoping & Setup with the requirement of / 20% - 40% PM / 40% Architect	Standard scoping with the requirement of mandatory 10% PM (remote)	Standard scoping with the requirement of 20% PM (remote or onsite)]

---
PoC Use Cases
- Scalability: add controllers and nodes
- Security: Authenticate against existing AD
- Interoperability: Integrate with existing Ceph cluster
- Accountablility: Measuring and Metering
- Useablility: Self Service Catalog
[Speaker Notes: For a PoC, a list of Use Cases should precede the Work Breakdown Structure. While these Use Cases are delivered very much like ordinary Work Packages, the customer will focus on these Use Cases for their buying decision. For non-PoC scopings this slide need to be deleted.]

---
Work Breakdown Structure
- Component 1
  - Work Package 1.1
  - Work Package 1.2
- Component 2
  - Work Package 2.1
  - Work Package 2.2
- Documentation and Organization
  - Meetings
  - Documentation
[Speaker Notes: This part is mandatory and may be extended if necessary. The WBS should include tasks and work packages that have to be performed / delivered by the customer. You may consider two variants of different WBS trees with different estimates and different levels of customer involvement / requirements.]

---
Work Package 1.1
- Red Hat supports the customer to/with ...
- Task One
- Task Two
estimated effort: 8 hours
Red Hat resources required: Consultant, Architect, PM
Customer resources required: Engagement Manger, Engagement Team
[Speaker Notes: Each item listed in the Work Breakdown Structure needs to be described as a Work Package. The entirety of all thes Work Packages is the WBS Dictionary (with the Work Packages as entries). The WBS Dictionary defines all work packages for the Engagement. These definitions include all tasks and resources. Every work package in the WBS is defined in the WBS Dictionary and will aid in resource planning and task completion. The Work Package should be described in a general manner to allow highest possible degree of re-useability. Please follow the guidelines for wording and terminology given in the Scoping Guidelines document: https://mojo.redhat.com/docs/DOC-1132682]

---
PoC Use Case: Deployment of OSP controllers and additional nodes
- Prepare additional Hardware
- Register with OSP Director
- Demonstrate deployment
estimated effort: 4 hours
Red Hat resources required: Consultant
Customer resources required: PoC Team, additional hardware node
success criteria:4th compute node is up and running in existing OSP cluster
[Speaker Notes: PoC Use Cases are pretty much the same as ordinary Work Packages. We should describe and agree upon success criteria for PoC Use Cases. For non-PoC scopings this slide needs to be deleted.]

---
WP Documentation and Organization
- Prep Call
- Meetings
- Daily Engagement Reporting
- Final Engagement Documentation
- Review and Lessons Learned Call
  estimated effort: 12 hours
  Red Hat resources required: Consultant, Architect, Project Manager / Coordinator
  Customer resources required: Engagement Manager, Stakeholders, meeting room
[Speaker Notes: The Documentation and Organization Work Package should be included in every WBS. If anyhow possible, each Friday but at least every second Friday the engagement should be reserved for this purpose and allow the Consultant to work off site.]

---
Effort Estimation
- Effort Estimation:
  - Architect: <XX> Mandays
  - Consultant: <XX> Mandays
- The estimated effort for this engagement in total is <XX> days.
- Red Hat offers all it’s engagement up to 20 days as a Packed Price (Fixprice).
[Speaker Notes: This part is mandatory and may be extended if necessary. Please use this slide for estimating total efforts for engagement <=20 days. There is a different template slide available for scoping engagements >20days. The Services Organization will add 10% of the WP effort for Project Management.]

---
Post PoC Use Case: Multi-Tier Application
- Prepare heat template to deploy 3-tier OXID shop application with load balancer, MariaDB backend and two tennant networks
- Integrate that application into CloudForms Service Catalog
- Demonstrate deployment
estimated effort: 8 hours
Red Hat resources required: none
Customer resources required: Admin, privileged access to hardware / Vms
Success of this use case is not relevant for the buying decision.
[Speaker Notes: Often the customer is interested in more Use Cases and features than we can deliver in a typical PoC time frame. To give the customer guidance for testing and using the PoC environment after our team has left the site, we may define Post-PoC use cases without success criteria. For non-PoC scopings this slide must be deleted. Even for PoC scopings this slide may be deleted.]

---
Constraints and Assumptions
The customer is responsible to provide certified hardware and sufficient Red Hat subscriptions for all software components related to this engagement.
If provided with an preparation document in advance of the engagement, the customer will make sure the appropriate steps are taken to ensure a seamless start.
[Speaker Notes: Summarize the constraints that must be considered. A constraint is an applicable restriction or limitation, either internal or external to the engagement, that will affect the performance of an engagement. The sponsor should be made aware of the constraints before making a funding decision List the assumptions to be taken into consideration. An assumption is something taken for granted or accepted as true without proof. The sponsor should be made aware of the assumptions before making a decision on funding the engagement Typical constraints include certain deadlines or dependencies for start and finish, resources to become available, approvals to be completed, ... Typical assumptions include subscriptions to be available, compute, network or storage resources to be available, ... This slide is mandatory.]

---
Project Coordination & Management Plan
- Red Hat will designate a skilled Project Manager (PM) or Project Coordinator (PC) who will be responsible for attunement of all Red Hat activities under this engagement.
- The customer will designate one Engagement Manager (EM) who is is authorized to make decisions regarding activities under this engagement.
- Primary contact for all communication with the Consultant on site is the Engagement Manger.
- EM and PM/PC will agree upon a series of calls and/or meetings in a preparation call that will take place in advance of the engagement.
[Speaker Notes: The Project Coordination and Management Plan is important to establish the RH PM and identify the primary and authoritative contact for the Consultant on site. In addition, the prep call should be advertised in this plan. This slide is mandatory.]

---
Scope Management Plan
The Work Breakdown Structure (WBS) and WBS Dictionary define the scope for this engagement.
Any member of the engagement team may initiate proposed scope changes. All change requests will be submitted to the Engagement Manager (EM) who will then evaluate and then accept or deny the requested scope change.
The EM is responsible for the acceptance of the final engagement documentation and engagement scope.
[Speaker Notes: The Scope Management Plan is an important tool to keep the engagement on track. It is quite common even in small engagements to work with “moving targets”. This slide is an agreement to avoid such scope changes to appear without notice. This is an insurance both for the Consultant (who otherwise may be in trouble reaching the given goal) and the Project Sponsor (who may have different objectives than the operational team the Consultant works with). This slide is mandatory.]

---
Schedule Management Plan
The delivery of work packages for this engagement will be scheduled by Red Hat GPS only after a purchase order has been signed. Details of the delivery schedule will be fixed usually within two working days after Red Hat has received the order.
A lag of 4 to 6 weeks between this scheduling and the availability of the Consultant should be expected.
Red Hat will perform Professional Services generally in cohered blocks of five days. The Consultant will be on site Monday to Thursday and the 5th day of the week (Friday) will be generally performed from remote and will be used for documentation, organization and successive preparation work.
[Speaker Notes: You usually don’t need to edit this slide. This slide includes important information to set expectations right. This part is mandatory.]

---
Engagement Staff Assignment
After finalizing this Proposal (Engagement Mangement Plan), Red Hat GPS will identify personnel with appropriate skills to deliver the Work Packages and best fit for the time constraints.
It is not possible that the work will be delivered by Red Hat partners.
It is not possible that the work will be delivered by an English speaking Consultant.
[Speaker Notes: You should discuss partner delivery and non native speaker topic with the customer and delete the appropriate sentences if necessary. This part is mandatory.]

---
Change Management Plan
The Change Management Board consists of the Engagement Sponsor, the Security Officer and the Engagement Manager.
The Red Hat Consultant and/or the Project Manager will provide information regarding modification of schedule, cost, risk and quality related with the requested change.
The Red Hat Consultant will continue to work following the existing Engagement Plan until the Change Management Board has formally accepted a change.
[Speaker Notes: You can delete this slide unless you have indication that this engagement will suffer from scope changes and moving targets.]

---
Risk Management Plan
Configuration changes on productive systems incur risks of data loss and loss of service availability.
To mitigate these risks the Customer will keep current backup data and allow for sufficient downtime to restore data in a fallback scenario.
No further risks are identified so far.
[Speaker Notes: Take a moment and think about potential risks for our customer arising from our engagement. Additionally, you should identify risks for Red Hat which need to be documented in the internal Engagement Scoping Form. A risk is defined as an uncertain event or condition that, if it occurs, has a positive or negative affect on the objectives. The sponsor should be made aware of the risks, including risks of not funding the engagement. The approach for managing risks for the Engagement includes a methodical process by which the delivering team identifies, scores, and ranks the various risks. Every effort will be made to proactively identify risks ahead of time in order to implement a mitigation strategy from the engagement’s onset. It may be advised to perform a data backup before starting. Rollback and failover scenarios may be required. If known before hand, the risks should be identified and mitigated. You may delete this slide if you are sure there are no risks to deal with.]

---
Quality Management Plan
The work provided by the Red Hat Consultant will be comprehensible documented.
To ensure highest Customer satisfaction, Red Hat will send out a survey after every engagement to the Engagement Sponsor via email. Red Hat would appreciate if the survey is filled out and returned after the engagement is fully delivered.
[Speaker Notes: Take a moment and think about the quality of our service and the deliverable. All members of the engagement team will play a role in quality management. It is imperative that the team ensures that work is completed at an adequate level of quality from individual work packages to the final deliverable. Quality control for the engagement will utilize tools and methodologies for ensuring that all deliverables comply with approved quality standards. You may delete this slide if you are sure that quality is not an issue.]

---
Supportability
For the avoidance of doubt, the results of the engagement described above are not part of Red Hat's products and therefore will not become subject to Red Hat's support or other elements of Red Hat's Software Subscriptions.
The same shall apply for any additional software components, which have been recommended by Red Hat Consulting and which are not part of Red Hat's products and support.
[Speaker Notes: Note that from a legal standpoint a dedicated written statement like this is not necessary. All support & maintenance relevant statements are part of Appendix1 (Chapter 1.4) and therefore not valid for our services as declared in Appendix3. Appendix is not part of a services OF and not related to our services contract / Order Form). Means that it's not mandatory even if I would strongly recommend it.]

---
Timeline and Milestones
- The engagement should start in calendar week <xx>
- Go life is scheduled for <xx>
- Stakeholders or required resources are unavailable
  - <role> and <date>
These dates are provided by the customer purely for informational purpose and in no way agreed part of the engagement.
[Speaker Notes: Identify the significant milestones or events in the engagement such as phases, stages, decision gates, or the approval of a deliverable. It presents a high-level engagement schedule. You may delete this slide if there are no such dates to consider.]

---
Stakeholders and Points of Contact
RH Project Coordinator / Manager
John Doe, PMP Red Hat, jdoe redhat.com +49 123 4567890
RH Solution Architect
John Doe, Solution Architect Red Hat, jdoe redhat.com +49 123 4567890
Engagement Manager
C. Customer, Head of IT ACME, ccustomer acme.com +49 123 4567890
Engagement Team
A. Admin, UNIX Operations ACME, aadmin acme.com +49 123 4567890
[Speaker Notes: Identify the stakeholders, both internal and external to the engagement. A stakeholder is a person or organization that is actively involved in the engagement and/or that could, positively or negatively, impact the achievement of the engagement objectives. The sponsor should be made aware of the stakeholders prior to making a funding decision.]

---
Location of Delivery
The engagement is delivered on the customer site
1313 Webfoot Walk, 98751 Duckburg
The consultant does not need a current ID card or passport for authentication.
Remote access is not possible.
[Speaker Notes: Statistics: The Engagement Plan Template consists of 22 slides. 8 slides are generic enough to stay unchanged in >80% of the cases. Additional 8 slides need to be filled with certain fields, names, numbers or addresses marked in red. Only the remaining 6 slides (#3 to #8) need to be edited in the sense of writing actual content. If more than one Work Package needs to be described, copies of the WP template need to be edited as well. 1 additional slide is added for >20day scopings. 3 additional slides are added to demonstrate the use of this template for PoC planning.]